## README
Review / Inspection Template
References & Applicable Documents
1
2
3
Generic Review Process
Phase |  | Description
Planning |  | The moderator fills the "Master Plan" (with help of author / project manager) and performs an entry check to make sure that the review object fulfills a minimum quality standard (e.g. spell check, clean compiled, template for review object was used by author).
Kick-Off (optional) |  | In a kick-off meeting, the author provides enough background information to the reviewers concerning review object and project environment so that each reviewer can reasonably find defects. The kick-off meeting is optional.
Checking |  | Each reviewer searches for defects and other problems in the review object and fills the "Checking" columns in the "List of Findings". The findings and the checking time are reported to the moderator. The moderator compiles all findings of all reviewers in one document, prepares the review meeting and fills parts of the "Data Summary".
Review Meeting |  | At the review meeting the team decides about the status of the findings. In the "Review Report" will be documented who will perform follow-up and whether a re-inspection is needed. Optionally the review meeting is followed by a "third hour meeting", where open issues can be discussed and where defects can be analyzed to obtain process improvement suggestions which prevent the occurrence of similar defects in the future.
Rework |  | The author corrects the defects.
Follow-Up |  | During the follow-up it will be checked whether all findings are solved as defined. The moderator closes the review and provides the "Data Summary" to quality assurance for statistics.
Copyright Notice & Template History of Change
Version | Date | Changed by | Description
1.3 | 2013-07-27 | P. Rösler | B3, B11-B13 in "Review Report" cleared
1.3 | 2013-03-09 | P. Rösler | Maintenance-No. (see hidden sheet "Maintenance") 5, 74, 76, 100, 102-104, 111, 112, 116, 125, 131-133
1.3 | 2013-02-27 | P. Rösler | Maintenance-No. 58, 77, 79, 86-95
1.2 | 2012-10-12 | P. Rösler | Design changes recommended by graphic designer Ruth Weiler, Berlin
1.2 | 2012-10-03 | P. Rösler | Maintenance-No. 69, 73, 81, 83, 84, English corrections
1.1 | 2012-08-26 | P. Rösler | Maintenance-No. 66-68, 70-72 solved
1.0 | 2012-08-15 | P. Rösler | Release for external use. 2012-08-15, Maud Schlich, Ralf Kneuper, Peter Rösler
0.2 | 2012-08-08 | P. Rösler | LoF new column "In Charge". Some Maintenance-No. solved.
0.2 | 2012-07-11 | P. Rösler | DS: table "Defect Summary by Status" added, DS: A37/A43: "per Unit" as formula
0.1 | 2012-06-28 | P. Rösler | MP and LoF: cells for checklists / scenarios added, DS: B5-B18 changed, DS: Auxiliary Cells added, DS: further minor changes. Other Maintenance-No. solved.
0.0 | 2011-12-13 | P. Rösler (ReviewConsult) | First version created based on templates from J. Flachs and T. Gilb. Review_Template_RC_en_v<x.x>.xlsx is the English version of ReviewConsult's review template. Check www.reviewconsult.de for newer versions of this template.
Copyright © 2011-2013 by ReviewConsult. Permission is granted to use, modify (including replacing the ReviewConsult logo by another logo), and distribute this template, as long as this copyright notice and the oldest history of change line (date 2011-12-13) remain part of the template.
← | Color Code, Template Maintenance Notes, Restrictions & Known Bugs
Color Code
Unit | Title cell, sometimes with explanatory comment
pp | Cell, in which data can be entered
pp/h | Calculated result
Template Maintenance Notes
0 | Open
Restrictions & Known Bugs
No. | Date | Entered by | Description
1 | 2013-03-07 | P. Rösler | Excel versions: The template is optimized for Excel 2003 for windows.
2 | 2013-03-07 | P. Rösler | Number of findings: In sheet DS some of the formulas use the number 9999. In consequence the formulas work only if there are less than approx. 9999 findings in sheet LoF.
3 | 2013-03-07 | P. Rösler | Entry and exit criteria: The template does not support the use of entry and exit criteria (i.e. there are no prepared cells for entry and exit criteria).
4 | 2013-03-07 | P. Rösler | Size of Review Objects: If more than one review object is entered in sheet MP and the review objects have different size units like "NLOC" and "pp", some of the cells cannot be used properly ("Size of Review Objects" in MP and roughly 4 cells in DS) .
5 | 2013-03-07 | P. Rösler | Drop down lists: The drop down lists in sheet LoF, columns "Review Object" and "Input from" are intentionally limited to display 8 entries (sparing the users the trouble of scrolling too much in the drop-down list). (See maintenance No. 2)
6 | 2013-03-07 | P. Rösler | Consistency between sheets MP and RR: In sheet RR there are approx. 15 cells, which get there contents from the corresponding cells in sheet MP. Format changes to the cells in MP (e.g. doublespaced cells or crossed out words) are not transferred automatically to the RR cells. (See maintenance No. 47)
7 | 2013-03-07 | P. Rösler | Consistency between sheets MP and RR: If lines are added to sheet MP to allow more than 3 review objects or more than 3 reference documents, sheet RR must be adapted accordingly.
8
9
10
Note on B4: E.g. inspection or quality assurance handbook of company
Note on A10: Based on book "Software Inspection" (Gilb & Graham, 1993) German description of the generic review process and other parts of the template: Book "Reviews in der System- und Softwareentwicklung – Grundlagen, Praxis, kontinuierliche Verbesserung" (Rösler, Schlich, Kneuper), planned publication date: autumn 2013
Note on B20: The following lines are not to be filled out by moderators or reviewers
Note on B38: Please click on the "+" symbol to open the hidden line(s).
Note on A42: np: net pages. 1 np = 300 "non-commentary" words, 1 np = 1 page of diagrams pp: print pages NLOC: non-commentary lines of code LOC: lines of code
Note on A47: Maintenance notes for excel beginners (Menue names from MS Excel 2003) To read the comments in the cells, please point the mouse cursor at the cell, but avoid pointing at the picture in the cell.
Note on B48: The hidden sheet "Maintenance" can be used to note and monitor planned template changes. Please use menue Format -> Sheet -> Unhide to display this sheet.
Note on A49: Some formulas in this template use names like "Size_of_Review_Object". To find out in which cells these names are defined, please use menu Insert -> Name -> Define. The name "Reviewer_abbreviations" is intentionally defined for the first eight reviewers only, sparing the users of the template the trouble of scrolling too much in the drop-down list in column "Input from" (sheet "LoF").
Note on B49: To set the color of cells depending on the cell content please use menue Format -> Conditional Formatting.
Note on C49: Design decision (2011-12-13 P. Rösler): The template does not use macros to make it easier for the users to understand the functioning of the template. Note: some of the "Restrictions & Known Bugs" can only be cured by use of macros.
Note on D49: To activate AutoFilter: Please select the desired range of title cells (e.g. "No." to "In Charge" in sheet "LoF") and use menue Data -> Filter -> AutoFilter.
Note on B50: Drop down lists can be defined by menue Data -> Validation (German: "Gültigkeit"). In tab „ error message“ it can be configured, whether only the values of the drop down list are allowed or as well different manual entries. "Ignore empty cells" might be deactivated.
Note on C50: The grey gridlines can be activated in a sheet by menue Tools (German: "Extras") -> Options -> View -> Gridlines.
Note on D50: 3 of the excel standard colors were changed in this template by menue Tools (German: "Extras") -> Options -> Color: Dark Yellow (German: "Dunkelgelb") to 201, 201, 201 (used for cell borders) Lime ("Gelbgrün") to 222, 235, 205 (used for title cells) Light Turqoise ("Helltürkis") to 213, 245, 251 (used for calculated cells)

## MP
Master Plan
Review No. | -
Project
Project Manager
Quality Manager
Moderator
Author(s)
Review Objects |  | Abbrev
1.
2.
3.
Reference Documents
1.
2.
3.
Checklists / Scenarios
1.
2.
Reviewers | Names (and Chapters to Review / Checklists or Scenarios to Be Used) | Abbrev
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.
Kickoff Meeting | Date / Time / Location
Checking |  | Unit
Send Findings until
Size of Review Objects
Opt. Check. Rate |  | /h
Opt. Check. Time | 0 | h
Review Meeting | Date / Time / Location
Additional Remarks
Note on A3: Usually not filled by moderator, will be filled by quality manager when the Data Summary is imported into the review database.
Note on A9: Insert more lines if necessary
Note on C9: Abbreviations to reduce the typing effort in the List of Findings
Note on A13: Reference Documents are the documents, to which the Review Objects have to be consistent. Insert more lines if necessary
Note on A17: Checklists and scenarios are auxiliary documents, which help the reviewers find more defects. Insert more lines if necessary
Note on C20: Abbreviations to be used in the List of Findings, column "Input from" The abbreviations need not to be identical to the phone directory.
Note on C33: np: net pages. 1 np = 300 "non-commentary" words, 1 np = 1 page of diagrams pp: print pages NLOC: non-commentary lines of code LOC: lines of code
Note on A35: Number of pages or lines to be reviewed (this may differ from the overall size of the review objects)
Note on A36: The optimum checking rate indicates how may pages or lines a typical reviewer can check in an hour. Benchmark data for code: 100-150 NLOC / h Benchmark data for text documents: - 1 to max. 2 np/h (Gilb & Graham 1993) - 2 to 3 pp/h for architecture and requirement documents (IEEE Std 1028-2008) (These data are counterintuitive, engineers would rather guess 5 to 10 pages per hour.)
Note on A37: Optimum checking time for a typical reviewer

## LoF
List of Findings
Checking | [6 empty] | Review Meeting, Rework and Follow-Up
No. | Review Object | Location of Finding | Finding Description | Checklist / Scenario Id. | Input from | Seve- rity | Comment | Status | In Charge / Date / ...
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
Note on A2: This has to be filled out by the reviewers during the individual checking
Note on H2: This has to be filled out during the review meeting, rework and follow-up.
Note on B3: Please use the abbreviations for the review objects.
Note on C3: The moderator may determine, how the location of a finding has to be specified. E.g. 023-026 if the finding refers to lines 23 to 26; p41 for page 41; 4.1.2 for chapter 4.1.2 If the finding occurs more than once in the review object (and it is too time-consuming to specify all locations), the wording "etc." or "ff." can be used. E.g. 023 etc.
Note on E3: If the finding was discovered via a checklist question or a scenario, please fill in the identification of this checklist question or scenario.
Note on F3: Please use the abbreviations for the reviewer names. If the finding was discovered in the review meeting, please enter "all".
Note on G3: Major: Defect, which possibly causes substantially higher costs, if it is found later in the development process. minor: Defect, which is not classified as a Major. ?: Question or the reviewer is very unsure whether the finding is a defect or a false alarm. note: Reviewer note which needs no author action. -: Used if Major, minor, ? and note are not appropriate (e.g. process improvement)
Note on H3: Meeting Comment / Action Item / Author Note (Resolution / Reason for Rejection, etc.) Field only filled if necessary
Note on I3: Open: The finding is valid and the author will deal with it in rework. Solved: The finding was solved (or no action was necessary). Rejected: The finding is rejected (false alarm). Postponed: The finding is valid but is postponed (and monitored in another list). Duplicate: The finding is the same as another finding. (This other finding is not marked as "Duplicate".) Note: exit criterion for rework: no "open" findings
Note on J3: Column for free use (please adjust the column for your special needs). Examples for use cases: - In preparation for the review meeting, the author can mark those findings with "Meeting", for which he/she needs a clarification or discussion. - In Follow-Up a reviewer can mark a finding with "t.b. re-discussed", if he/she does not agree with the author's solution.

## DS
Data Summary
Review Effort | [7 empty] | Auxiliary Cells for Calculating Time Efforts
Reviewers | Checking Times (h) | Other Times (h) | Review Meeting Duration (h) | No. of Partici-pants | Time for Review Meeting (h) | Rework Time (h) | Total Review Effort (h) | From | To | Break | No. P. | Effort (hh:mm) | Effort (h)
1. | [10 empty] | 1 | 0:00 | 0
2. | [10 empty] | 1 | 0:00 | 0
3. | [10 empty] | 1 | 0:00 | 0
4. | [10 empty] | 1 | 0:00 | 0
5. | [10 empty] | 1 | 0:00 | 0
6. | [7 empty] | Total |  |  |  | 0:00 | 0
7.
8.
9.
10.
Moderator
Author
Total | 0 | 0 |  |  | 0 |  | 0
Number of Defects and Efficiency | [5 empty] | Review Objects
Severity | Number of Defects | % | Efficiency (Defects found / h) | Defects found per |  | Size | Unit
Major | 0 | 0% | 0 | #DIV/0! |  | 0 | 0
minor | 0 | 0% | 0 | #DIV/0!
? | 0 | 0% | 0 | #DIV/0!
note | 0 | 0% | 0 | #DIV/0!
- | 0 | 0% | 0 | #DIV/0!
Total | 0 | 0% | 0 | #DIV/0!
Defect Summary by Status
Severity | Open | Solved | Rejected | Postponed | Duplicate | Total
Major | 0 | 0 | 0 | 0 | 0 | 0
minor | 0 | 0 | 0 | 0 | 0 | 0
? | 0 | 0 | 0 | 0 | 0 | 0
note | 0 | 0 | 0 | 0 | 0 | 0
- | 0 | 0 | 0 | 0 | 0 | 0
Total | 0 | 0 | 0 | 0 | 0 | 0
% | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0! | #DIV/0!
Effectiveness Estimations
Estimation by Comparing the Actual vs. the Optimum Checking Time
Achiev. Effec-tiveness | Necess. No. of full Reviewers | Opt. Check. Time (h) | Actual Check. Time (h) | Effective-ness | Majors found | Total Majors before | Remain. Majors
|  | 0 | 0 | #DIV/0! |  | #DIV/0! | #DIV/0!
per |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Estimation by Capture-Recapture Method / "Fish Pond Method"
| Reviewer A | Reviewer B | Duplicates C | Effective-ness | Majors found F | Total Majors T = A*B/C | Remain. Majors
|  |  |  | #DIV/0! | 0 | #DIV/0! | #DIV/0!
per |  |  |  |  | #DIV/0! | #DIV/0! | #DIV/0!
Review Savings Estimations
Estimation based on Individual Major Defects
Finding No. | Estimated Time for find&fix the Defect later (h) | Expert / Comment |  | Saved Time for all Majors (h) | Total Review Effort (h) | Time saved by this Review (h) | ROI
all other Majors
Total | 0 |  |  | 0 | 0 | 0
Estimation based on Mean Value
Majors found | Estimated Time for find&fix a Major later (h) | Expert / Comment |  | Saved Time for all Majors (h) | Total Review Effort (h) | Time saved by this Review (h) | ROI
0 |  |  |  | 0 | 0 | 0
Note on J4: These cells do not effect other cells in the template. Calculated results have to be transferred manually. Typical use case for these cells: A reviewer fills in the start and end time for checking and possible break times. The effort in hours (in decimal format) can now be entered into the "Checking Times" in column B.
Note on B5: Effort for Individual Checking Will be provided by the reviewers after individual checking. Accuracy +-10% is good enough. The privacy policy of your company may require, that individual checking times are not electronically stored and processed. In this case you as a moderator could gather the individual checking times orally and enter the sum of the checking times (in the "Total" line) manually.
Note on C5: Effort for Planning / Kickoff / Follow-Up / etc. Will be provided by the participants. Not included are times for the Review Meeting, checking times and the author's rework time.
Note on D5: Actual duration of review meeting
Note on E5: No. of review meeting participants
Note on G5: How many hours did the author spend on correcting the findings. If you don't want to wait until author's rework is done, please enter an estimated value.
Note on J5: Format hh:mm Shortcut Strg+Shift+"."
Note on K5: Format hh:mm Shortcut Strg+Shift+"."
Note on L5: Format hh:mm
Note on M5: No. of participants
Note on B22: Duplicates and rejected findings not counted
Note on H22: see Master Plan
Note on D23: Benchmark data: 1 Major / h ("Software Inspection" 1993, p315, MEL inspection data)
Note on G32: Duplicates and rejected findings included
Note on A45: For a description of the method see book "Reviews in der System- und Softwareentwicklung – Grundlagen, Praxis, kontinuierliche Verbesserung" (in German). For a description of a similar estimation method see www.reviewtechnik.de/SW-QS-Tag-2010_Stichproben-Reviews_Roesler_Schlich_v1.5_pub.ppt, slides 38-45 (in German)
Note on A46: Rule of thumb for achievable effectiveness: 50%. About 50% of the Major defects in the document will be found by the review team, if the optimum inspection rate is obeyed. The rule of thumb can be fine tuned, if you consider the maturity level of your review process or of your development process. Fagan, sd&m-Conference 2001: “When people implement inspections right away they might find 50 or 60% of all the operational defects. ... When you refine the inspection process that you dealing with, ..., they find between 75 and 85% of all operational defects before any testing. Some of them are finding more than 90% if they are exceptional cases.” www.gilb.com (Forum, as of 23.09.2005), Topic “Insp., Qual. Control”, Thread “Completeness of candidate doc.”, Posting Kai Gilb 17.09.2004: “We have found Inspection to operate in the area of about 3% (the normal for inspections not optimized with optimal checking rates etc.) to about 88%.”
Note on B46: Necessary number of full reviewers to achieve the Achievable Effectiveness. Full reviewer: reviewer who has the knowledge to check all parts of the review object. Rule of thumb: Necessary number of full reviewers = 2.5 to 3 (estimation by P.Rösler, 2011) Benchmark data: A company reported that for code reviews 4 or more reviewers did only find negligible more defects than 3 reviewers.
Note on C46: Optimum checking time (total for all reviewers)
Note on D46: Actual checking time (total for all reviewers)
Note on E46: Effectiveness Definition: Effectiveness = Major defects found / all existing Major defects Effectiveness Estimation (P. Rösler, 2011): Effectiveness = Achievable Effectiveness * Optimum Checking Time / Actual Checking Time
Note on F46: Number of Major defects found in the review object (don't count Major defects in the reference documents). Caution: too many Majors found in the meeting (provided by "all") will destort the estimate.
Note on G46: Estimated number of Major defects before review = Majors found / Effectiveness Benchmark data ("Software Inspection" 1993, p385, MEL inspection data): "Default expectation: before Inspection, for documents never Inspected, and which have been written by authors without Inspection experience for that document type: 10-20 major defects per page. For mature process documents we would expect fewer than 0.5 majors per page before checking. "
Note on H46: Remaining Major defects after rework (assuming that all corrections done by author are correct)
Note on H48: so called "remaining Major defect density"
Note on A51: For a description of the method see book "Reviews in der System- und Softwareentwicklung – Grundlagen, Praxis, kontinuierliche Verbesserung" (in German) or www.reviewtechnik.de/SW-QS-Tag-2010_Stichproben-Reviews_Roesler_Schlich_v1.5_pub.ppt, slides 47-50 (in German)
Note on B52: A = Number of Majors (including duplicates) found by reviewer A in the review object (don't count Major defects in the reference documents). Reviewer A is the reviewer, who found the most Majors.
Note on C52: B = Number of Majors found by reviewer B The other reviewers constitue "reviewer B". Duplicates within this group are not counted, only duplicates to reviewer A.
Note on D52: C = Number of Majors, which were found by both reviewers. Caution: This is not necessarily the number of Major findings with status "duplicate".
Note on E52: Caution: if the number of duplicates (C) is low (e.g. 1,2,3), then the result is very arguable. Caution: Majors found in the meeting (provided by "all") will destort the estimate. The real effectiveness will be higher in this case.
Note on F52: Number of Majors found: F = A + B - C This number does not include the Majors, which were found in the review meeting (provided by "all").
Note on G52: Estimated number of all Majors in review object: T = A * B / C
Note on A60: Experts estimate for the worst 1, 2 or 3 found Major defects, how much time it would have cost to find and fix each of them later in the project. The other Major defects are estimated across-the-board.
Note on A61: No. of the examined Major defect in the "List of Findings"
Note on C61: Expert who provided the estimation and/or any comments concerning the estimation
Note on H61: Return on Investment If greater 0, then the review saved project effort.
Note on B70: Mean value for find&fix a Major later Admittedly this is the difficult part of the estimation as long as there are no historical data of projects in the company (e.g. in a defect tracking tool) . Benchmark data ("Software Inspection" 1993, p315, MEL inspection data): 9.3 work-hours Benchmark data from another company (source: P. Rösler 2011): Default statistic value for every defect not found is - if the review is done in the Requirements phase: 50 h. - if the review is done in the Analysis & Planning phase: 30 h. - if the review is done in the Implementation phase: 8 h. - if the review is done in the System Test phase: 2 h.

## RR
Review Report
Date of Report
Project
Moderator
Review Objects
1.
2.
3.
Review Decision
made by
Follow-Up of Rework by
Re-Inspection needed
Reviewers | Names (and Chapters to Review / Checklists or Scenarios to Be Used)
1.
2.
3.
4.
5.
6.
7.
8.
9.
10.
Additional Remarks
Note on A6: Insert more lines if necessary
Note on A12: Please select (or enter name of specialist who performs Follow-Up)

## Maintenance (hidden)
Issue List for Maintenance / further Development of this Template
No. | Review Object | Location of Finding | Finding Description | Checklist / Scenario Id. | Input from | Seve- rity | Comment | Status | In Charge / Date / ...
1 | LoF | title line | Autofilter geht nur mit zusammenhängendem Bereich. |  | ros |  | leider | Rejected
2 | LoF |  | Auswahlfeld für Reviewobject und "Input from" sieht etwas seltsam aus |  | ros |  | Mentioned in README, Restrictions & Known Bugs | Postponed
3 | MP |  | internationalere Reviewer-Namen |  | ros |  |  | Postponed
4 | MP |  | Logo verankern, damit es bei Spaltenverbreiterung am Platz bleibt |  | ros |  | Zu viel Aufwand | Rejected
5 | MP & RP |  | "Additional Remarks" Felder sind unpraktisch |  | ros |  | ROS 27.02.2013: Auf eine Zeile reduziert, die 4 Zeilen hoch ist. Nachteil in Kauf genommen, dass beim Anpassen der Höhe durch Doppelclick die Höhe auf eine Zeile zurückfällt. | Solved
6 | DS |  | Feld "Time for Review Meeting (h)" kann auch weggelassen werden |  | ros |  |  | Rejected
7 | DS etc. |  | Felder mit Formeln, also Felder, die nicht ausgefüllt werden sollen, sind derzeit mit helltürkis gefüllt. Evtl. gibt es eine gestalterisch schönere Farbe. |  | ros |  | ausprobiert, es kommt nur hellgrün oder hellgelb in Frage, aber helltürkis kommt mir minimal besser vor. Vgl. aber No. 73 | Rejected
8 | MP |  | Zeilen "Kickoff", "Checking", "Review Meeting": Überschriften wie "Meeting Date/Time/Location" evtl. nicht in Spalte B, sondern in Spalte A eine Zeile drunter positionieren. |  | ros |  | ausprobiert, sieht schlechter aus. | Rejected
9 | DS |  | prüfen, wie die helltürkisen Felder aussehen, wenn Template komplett leer ist (gibt es DIV0 oder so was). |  | ros |  | wenn alles leer ist steht überall 0. OK (ThMo) | Solved
10 | DS |  | Reworkfeld könnte man einsparen, weil es Feld C16 für Autor gibt |  | ros |  |  | Rejected
11 | alle Blätter |  | Einfügen->Namen: prüfen ob alles benötigt wird (je Blatt unterschiedlich). Ebenso dass keine überflüssigen Makros drin sind. Und wie die Druckansicht aussieht (Datei->Seitenansicht). |  | ros |  | zuletzt erl. 06.07.2012 | Solved
12 | MP |  | Name Reviewer_Abbr nicht richtig definiert. Genauso Document_abbreviations |  | ros |  |  | Solved
13 | LoF |  | Spalte Input from: falsche Eingaben werden nicht angemotzt (was vielleicht ok ist, aber ich verstehe Gültigkeitsdefi. nicht ganz, bei Severity verhält es sich anders, weil Quelle keine Namensdefinition ist, sondern eine konkrete Aufzählung) |  | ros |  | Es ginge mit ""Leere Zellen ignorieren" nicht auswählen". Nichts tun, denn sonst wird "all" auch angemotzt | Rejected
14 | README |  | erklären was blaue Felder bedeuten |  | ros |  | Dup. zu 116 Warten, ob überhaupt jemand damit auf die Schnauze fällt | Duplicate
15 | alle Blätter |  | Simulieren, wie es über Beamer aussieht, bei LoF reicht 800*600 nicht. |  | ros |  | Workaround im wirklichen Leben ist: Zoom ändern oder Spalten D und G schmaler machen | Solved
16 | DS, MP |  | In Feldern wo ich Unit reinbaue, wird Zeilenhöhe nicht automatisch angepast |  | ros |  | Betrifft nur MP, Opt. Check. Rate | Rejected
17 | MP | B30&31 | 0 Dezimalstellen bei NLOC wäre schöner |  | ros |  |  | Postponed
18 | LoF |  | Location evtl. linksbündig |  | ros |  | sieht schlechter aus | Rejected
19 | MP | C32 u.a. helltürkise Felder | evtl. Feld vor ungewollten Änderungen schützen. Gilt evtl. auch für andere Tabellenblätter. |  | ros |  | dup. zu No. 21 | Duplicate
20 | README |  | Exit ist keine separate Phase. Allgemein: die Beschreibung sollte im Prinzip identisch zur Website sein. |  | ros, msc, rkn, awg |  | 28.06.2012 ROS | Solved
21 | alle Blätter |  | Zellenschutz verwenden vor allem für blaue Felder |  | ros, msc, rkn, awg |  | Hab's an Blatt DS ausprobiert (Review_Template_RC_v0.2_filled_tmp-TestBlattschutz.xlsx). Mir gefällt nicht, dass Benutzer dann die leeren Felder nicht formatieren kann. Befürchte weitere Nebeneffekte, die den Nutzen überwiegen. ROS 03.07.2012. MSC 20.07.2012: aus meiner Sicht ok | Rejected
22 | LoF |  | Spalte "Input from" wollen wir evtl. nicht. |  | ros, msc, rkn, awg |  | Da waren Datenschutzüberlegungen ein Grund. In der Praxis braucht man die Spalte aber. | Rejected
23 | LoF |  | Severity: "-" ist unsprechend, warum nicht gleich "Vorschlag" nennen? |  | ros, msc, rkn, awg |  | "Vorschlag" ist nur eine der Möglichkeiten unter "-". "-" ist zwar unsprechend, aber optisch sehr sprechend. | Rejected
24 | LoF |  | wir hatten zuletzt 2 Commentspalten vereinbart |  | ros, msc, rkn, awg |  | 28.06.2012 ROS: stimmt, aber ich will die Breite des Blatts LoF nicht vergrößern, weil es so auf bestimmten Bildschirmen noch komplett draufpasst. In der Praxis reicht auch eine Spalte. | Rejected
25 | LoF |  | Status: wir hatten evtl. mehr Stati |  | ros, msc, rkn, awg |  | 28.06.2012 ROS: ich mache erst was, wenn uns ein Status konkret abgeht. | Rejected
26 | LoF |  | Warum Logo nicht rechtsbündig? |  | ros, msc, rkn, awg |  | 28.06.2012 ROS | Solved
27 | LoF |  | Höhe von Zeile 3 evtl. verringern |  | ros, msc, rkn, awg |  | 28.06.2012 ROS: geht nimmer wg. Feld "Checklist / Scenario Id." | Rejected
28 | LoF |  | Idee: Logo evtl. nur in Kopfzeile (Nachteil: nur bei Druck sichtbar) |  | ros, msc, rkn, awg |  | 28.06.2012 ROS | Rejected
29 | RP | B12 | Moderator auch aufführen |  | ros, msc, rkn, awg |  |  | Solved
30 | RP |  | MSC sucht raus, welche Felder fehlen (z.B. Reference Documents, oder Kriterien gegen die geprüft wurde) |  | ros, msc, rkn, awg |  | erl. durch Diff_RC-v0.0_filled_zu_RC-MSC_v0.4_deutsch.xlsx | Solved
31 | MP | A13 | Refe. Doc. / Criteria |  | ros, msc, rkn, awg |  | 28.06.2012 ROS: Nutzen ist mir zu klein gegenüber dem Umfangreicherwerdens des Templates. | Rejected
32 | RP |  | RP klingt nach Rheinland Pfalz, warum nicht RR oder Rep? |  | ros, msc, rkn, awg |  | Solved incl. README D27 | Solved
33 | DS | Z 6 | Spalten D ff sehen so aus, als ob es zu Reviewer 1 gehört (gestalterisch) |  | ros, msc, rkn, awg |  | Stimmt zwar, aber die Alternative (s. Review_Template_RC-MSC_v0.4_deutsch.xlsx) erschwert die optische Zuordnung der Felder zu der Titelzeile. 05.07.2012 ROS: doch noch solved, s. No. 54 | Duplicate
34 | DS | G6 | Rework Time gehört nicht in die Reviewzeiten |  | ros, msc, rkn, awg |  | ros: bei Telko zu diskutieren, bin anderer Meinung. 28.06.12: meine mich zu erinnern, dass der Vorschlag keine Mehrheit fand, daher ->rejected | Rejected
35 | DS | B28 | Diese Total sind weniger als in LoF, weil Dup & Rej fehlt, evtl. Zwischen-Totals ausweisen |  | ros, msc, rkn, awg |  | ROS 28.06.12: Wenn dann gleich aus Firma1 "Defect Summary by Status" übernehmen. 02.07.12 ROS: table "Defect Summary by Status" added | Solved
36 | RC-Website |  | DS A34: warum Vortrag nicht auf RC-Homepage ablegen? |  | ros, msc, rkn, awg |  | Nur in Zusammenhang mit einer Homepage-Erweiterung miterledigen. ROS 03.07.2012 | Postponed
37 | DS | B35 | Kommentar: "neccess.." typo (2 mal) |  | ros, msc, rkn, awg |  |  | Solved
38 | DS | C35 | Feldname wird in MP mit anderer Bedeutung verwendet |  | ros, msc, rkn, awg |  | ROS: Stimmt, im MP als Zeit pro Reviewer, im DS als Zeit für alle Reviewer. Mit fällt aber keine unverkrampfte Lösungsmöglichkeit ein und ich erwarte vom "User" keine Fehlinterpretation. (ROS) ROS 09.03.2013: habe klarstellende Kommentare in beide Felder eingefügt. | Solved
39 | DS | B35 | Was soll ein halber Reviewer sein? Das ist mindestens nicht nachvollziehbar. |  | ros, msc, rkn, awg |  | Will ich im Template nicht erläutern, muss Bestandteil eines noch zu schreibenden Buches sein. (ROS) | Rejected
40 | DS | F36, Z. 22-28 | Feld F36 kann automatisch berechnet werden und in Z 22-28 können die Mj in Reference Documents separat ausgewiesen werden. |  | ros, msc, rkn, awg |  | Stimmt zwar, aber der "Programmier"-Aufwand ist mir zu hoch. (ROS 28.06.12) | Rejected
41 | DS | A37 (v0.2: A48, A54, E11) | "per Unit" ersetzen durch Formel die z.B. "per NLOC" ausgibt |  | ros, msc, rkn, awg |  | Der Nutzen ist mir zu klein im Verhältnis zur Verkomplizierung der Wartung des Templates. (ROS 28.06.12) msc/ros: ros soll erneut nachdenken. ROS 02.07.2012: solved. | Solved
42 | MP, LoF |  | Beschluss 06.06.12: Hilfsdokumente einbauen |  | msc, ros |  |  | Solved
43 | MP | A31 | Beschluss 06.06.12: aus ROS-Zweig: "s" ergänzen |  | msc, ros |  |  | Solved
44 | DS | B6ff | Beschluss 06.06.12: Diagonal wegnehmen |  | msc, ros |  |  | Solved
45 | DS | A21,B22 | Beschluss 06.06.12: aus ROS-Zweig, evtl. "numbers" |  | msc, ros |  |  | Solved
46 | DS |  | Beschluss 06.06.12: Hilfsrechner kommt rein, ohne Datum |  | msc, ros |  |  | Solved
47 | RR | B15 und andere türkise Felder | Wenn diese Felder im MP zweizeilig gefüllt werden, wird die Feldhöhe in RR nicht automatisch erhöht. 28.06.2012 |  | ros |  | Mentioned in README, Restrictions & Known Bugs ROS: Makros wie in http://www.office-loesung.de/ftopic234187_0_0_asc.php vorgeschlagen will ich nicht einbauen, das bleibt ein "known bug". ROS 03.07.2012 | Rejected
48 | alle Blätter |  | Logo nicht gleich groß und gleich positioniert |  | ros |  |  | Solved
49 | LoF |  | Wie in Blatt Maintenance zu sehen, ist eine weitere Spalte ("Follow-Up nötig J/N" oder "Wiedervorlage für" oder ähnlich) dann nötig, wenn es ein mehrfaches Hin-und-her zwischen Rework und Follow-Up gibt (was im Review-Prozess nicht abgebildet ist) |  | ros |  | Will keine Spalte für seltene Fälle einbauen. ROS 03.07.2012 Aber vgl. No. 62 | Rejected
50 | DS |  | Tab. "Defect Summary by Status": Spalte Total evtl. als letzte Spalte |  | ros |  |  | Solved
51 | README |  | Coypright-Vermerk (bzw. anti-copyright notice) einbauen, wenn wir das Template breit streuen wollen. http://en.wikipedia.org/wiki/Copyleft |  | ros |  | Vgl.: Copyright © 2001 by Karl E. Wiegers. Permission is granted to use, modify, and distribute this document. http://www.cs.toronto.edu/~sme/CSC444F/handouts/inspection_issue_log.pdf | Solved
52 | README | C7 | "so that each reviewer can reasonable find defects" --> " reasonably" |  | ros |  |  | Solved
53 | DS | A48-E48, A54-E54 | gestalterisch evtl. noch nicht einheitlich zum Rest. Ebenso die fette Linie zwischen Zeilen 47/48, 53/54 |  | ros |  |  | Solved
54 | DS | D6-H6 | wg. gestalterisch nach Zeile 18 verschieben? Vgl. E66-H66 |  | ros |  | dup. zu No. 33 | Solved
55 | MP | B5/C5-B8/C8 | Zellen aufsplitten, damit falls gewünscht die Abbrev. für diese Personen leichter eingebaut werden kann |  | ros |  | für B3/C3-B8/C8 gemacht. ROS 04.07.2012 | Solved
56 | README |  | Temp. Maint. Notes sind noch in deutsch |  | ros |  |  | Solved
57 | LoF |  | In der "filled"-Datei sind die Findings alle auf deutsch |  | ros |  | Umgangen durch Kommentare in MP, A41-A42 | Solved
58 | LoF |  | In der "filled"-Datei sind die Findings aus einem Seminarübungsbeispiel von ROS. Wer die Findings liest und dann zeitnah das Seminar besucht, findet mehr Fehler als sonst zu erwarten wäre. Beachte auch Buchproblematik. |  | ros |  | (ehem.: Risiko wird in Kauf genommen) Auch "Reflighting" ersetzen. Mindestens einige Mj verändern. Anzahl darf sich wg. DS nicht ändern. | Solved
59 | README |  | Erwähnen, wo man die neueste Version des Templates downloaden kann? |  | ros |  | "Check www.reviewconsult.de for newer versions of this template" in Datei->Eigenschaften | Solved
60 | alle Blätter |  | Prüfen, welche verbundene Zellen man auflösen kann, denn verbundene Zellen haben gewisse Macken. |  | ros |  | zuletzt erl. 05.07.2012 | Solved
61 | Datei |  | Dateinamen festlegen Review_Template_RC_de_v1.0.xlsx Review_Template_RC_de_v1.0_filled.xlsx Review_Template_RC_en_v1.0.xlsx Review_Template_RC_en_v1.0_filled.xlsx Review_Template_RC_v1.0-de.xlsx Review_Template_RC_v1.0-de_filled.xlsx Review_Template_RC_v1.0-en.xlsx Review_Template_RC_v1.0-en_filled.xlsx Review_Template_RC_v1.0.xlsx Review_Template_RC_v1.0_filled.xlsx Review_Vorlage_RC_v1.0.xlsx Review_Vorlage_RC_v1.0_ausgefüllt.xlsx |  | ros |  | MSC, ROS: 1. Variante nehmen wir. Seiteneffekt auf History of Change v0.0 beachten. ROS 20.07.2012 Solved | Solved
62 | LoF | Status-Spalte | Folgende in der Praxis sinnvolle Abweichung vom Standard-Reviewprozess wird derzeit nicht durch unser Template unterstützt: Für den Fall, dass Autor vor der Sitzung die Findings liest und bewertet, brauchen wir weitere Stati wie Open_and_to_be_discussed oder Open_and_accepted. 08.07.2012 Vgl. No. 49: "Wie in Blatt Maintenance zu sehen, ist eine weitere Spalte ("Follow-Up nötig J/N" oder "Wiedervorlage für" oder ähnlich) dann nötig, wenn es ein mehrfaches Hin-und-her zwischen Rework und Follow-Up gibt (was im Review-Prozess nicht abgebildet ist)" ROS-Vorschlag, wie es mit vorhandenen Stati geht: Wenn der Autor vor dem Meeting die Findings bewertet, bedeutet: - Open = Open and accepted, keine Diskussion nötig - Solved = accepted und sogar schon solved, keine Diskussion nötig (Wie kennzeichnet man aber "solved und will im Meeting zeigen, wie"? Antwort: Status leer lassen und im Comment schreiben: Solved) - Rejected: Diskussion ist sowieso sinnvoll - leerer Status: Diskussion wie bei normalem Reviewprozess, kann im Meeting zu Open, Rejected etc. werden. Nachteil des Vorschlags: es ist intuitiv unplausibel, dass man in der Sitzung gerade die "Open" nicht diskutiert. Man muss es so sehen: Am Ende der Sitzung muss jedes Finding einen Status haben, die Zeilen mit "Open" haben schon einen Status, also müssen gerade die anderen Zeilen besprochen und mit Status versehen werden. |  | ros |  | MSC 20.07.2012: doch überlegen, ob weitere Status sinnvoll. Z.B. In Work. ROS 20.07.2012: es läuft auf eine Zusatz-Spalte "In Charge" o.ä. raus. Neue Stati allein haben unschöne Seiteneffekte auf DS Zeilen 31 ff. Solved: LoF new column "In Charge" MSC: ROS: evtl. Author/Reviewer weg und Follow-Up rein. Solved 08.08.2012 | Solved
63 | DS |  | Evtl. Zeile 6 bis 17 gruppieren? |  | ros |  | Macht DS etwas häßlicher und wird wohl kaum gebraucht. | Rejected
64 | DS | G21 | Mehrzahl? Auch Kommentar in MP, A34 |  | ros |  |  | Solved
65 | README | A24 | Copyright 2011-2012 |  | rkn |  |  | Solved
66 | 1.0 LoF | H2 | Follow-Up verwendet die Spalten auch. Kommentar stimmt auch nicht ("after"). |  | ros |  |  | Solved
67 | 1.0 LoF | Zeile 103 | überlegen, ob Zeile unten einen gestrichelten Rahmen haben soll wie alle anderen Zeilen drüber |  | ros |  |  | Solved
68 | 1.0 LoF | C3 Kommentar | "4.1.2," -> "4.1.2" |  | ros |  |  | Solved
69 | 1.0 LoF | C3 Kommentar | "If the finding occurs more than once in the review object (and it is too time-consuming to specify all locations), the wording "and others" can be used." -> besser weil kürzer evtl. "etc." |  | ros |  |  | Solved
70 | 1.0 RR | B14 | hat nicht denselben Text wie MP B20. Evtl. sollte hier und bei ähnlichen Feldern der Inhalt aus MP formelmässig übernommen werden. |  | ros |  |  | Solved
71 | 1.0 DS | Zeilen 23-27, 33-37 | Spalte I statt J muss abgefragt werden |  | ros |  |  | Solved
72 | 1.0 DS | Zeilen 47, 53 | Effectiveness Estimations: Anzahl Majors found so setzen, dass bei "Total Majors before" ungefähr 21 herauskommt (konsistent zu B23) |  | ros |  |  | Solved
73 | 1.0 | alle Blätter | Farben sind schrecklich und behindern Verbreitung des Templates. Blau passt nicht zu grün, das grün ist zu kräftig. |  | flj |  | Mit Extras->Optionen->Farbe folgende Standardfarben geändert: Gelbgrün nach 222, 235, 205 (Überschriftenfelder) Dunkelgelb nach 201, 201, 201 (Feldrahmen) Helltürkis nach 213, 245, 251 (berechnete Felder) | Solved
74 | 1.1 | README | Evtl. "Template Maintenance Notes" -> "Restrictions, Known Bugs & Template Maintenance Notes" |  | ros |  |  | Solved
75 | 1.1 | README | Falls wir benutzerdefinierte Farben verwenden (ja: No. 73), muss diese Tatsache in "Template Maintenance Notes" dokumentiert werden |  | ros |  |  | Solved
76 | 1.1 | README | Evtl. Bereich einfügen mit "References & Applicable Documents", dazu gehören z.B. Review-Datenbank, Reviewhandbuch, Qualitätssicherungshandbuch |  | ros |  |  | Solved
77 | 1.2 | README | C11: "During the follow-up it will be checked whether all findings are solved as defined during the review meeting." will Reviewer geändert haben in: "During the follow-up it will be checked whether all findings of the review meeting are solved as defined." Anderer Reviewer will: "During the follow-up it will be checked whether all findings of the review meeting are solved as defined." |  | ros |  | 09.11.2012 ROS. MSC: "During the follow-up it will be checked whether all findings are solved as defined." | Solved
78 | 1.2 | MP | C20: "Abbreviations to be used in the List of Findings, " will Reviewer geändert haben in: "Abbreviations are to be used in the List of Findings, " |  | ros |  | 09.11.2012: MSC, ROS: rejected | Rejected
79 | 1.2 | README | C7: Reviewer will "In a kick-off meeting, the author provides as much background information as possible to the reviewers" |  | ros |  | 09.11.2012 MSC, ROS: In a kick-off meeting, the author provides enough background information to the reviewers concerning review object and project environment so that each reviewer can reasonably find defects. | Solved
80 | 1.2 | README | C9, C11: Reviewer will "Follow-up" statt "follow-up". |  | ros |  | 09.11.2012: MSC, ROS: rejected | Rejected
81 | 1.2 | MP etc. | A3-A8 etc.: Einzug (nach links) vergrößern, sonst pappt Schrift am Rahmen. |  | ros |  |  | Solved
82 | 1.2 |  | Ruth Weiler: sie würde noch folgende Änderungen überlegen: - DS: alle Total-Zahlen fett, die großen fetten Zahlen normal groß und rot. - DS: D5 & F5: "h" soll nicht einzeln stehen |  | ros |  | ROS 27.02.2013: rejected | Rejected
83 | 1.2 | DS | O11 Format falsch |  | ros |  |  | Solved
84 | 1.2 | LoF | beim Drucken entsteht schwarzer Rahmen |  | ros |  |  | Solved
85 | 1.2 | LoF | In Tabelle LoF sollen wohl die Ergebnisse von verschiedenen Prüfern konsolidiert werden. Dann halte ich es für ungeschickt, die Einträge nur mit einer laufenden Nummer zu versehen. Es sollte vielmehr schon gleich jeder Prüfer dazu angeregt werden, eindeutige Kennungen mit Kürzel und Nummer zu vergeben. |  | H.T. 15.10.12 |  | ROS 05.03.2013: in Abwägung von diesem kleinen Vorteil mit dem Bedarf, das neue Verfahren beschreiben und vermitteln zu müssen, mache ich lieber nichts. | Rejected
86 | 1.2 | Datei | Review_Template_RC_en_v1_2 sollte beim Öffnen das README Blatt zeigen. |  | M.S. 16.10.12 |  | ros 17.10.2012: wäre bei öfterem Gebrauch von Reviews lästig. | Rejected
87 | 1.2 | Datei | Abkürzungen in den Blatt-Taben (MP, LoF, DS, RR) durch ausgeschriebene Bezeichnungen ersetzen |  | M.S. 16.10.12 |  | ros 17.10.2012: war Absicht, bleibe dabei | Rejected
88 | 1.2 | Datei | Bei Stellen der Form „A/B“ gehört um den ‚/‘ kein Leerzeichen |  | M.S. 16.10.12 |  |  | Solved
89 | 1.2 | README | Phase Planning, „make sure that the“ => “make sure the” |  | M.S. 16.10.12 |  | ROS 05.03.2013: war von Englischkorrekturlesern nicht kritisiert worden. | Rejected
90 | 1.2 | README | “In a kick-off meeting the author” => “The author provides … during a kick-off meeting.” |  | M.S. 16.10.12 |  | ROS 05.03.2013: ich belasse es. | Rejected
91 | 1.2 | LoF | “List of Findings” => “Findings” ist ausreichend |  | M.S. 16.10.12 |  | ros 17.10.2012: stimmt zwar, aber "historisch" eingebürgert | Rejected
92 | 1.2 | Maintenance | alle Spalten wie bei LoF einführen, Format von LoF übernehmen. |  | ros |  | ros 17.10.2012 | Solved
93 | 1.2 | Mails | Evtl. neues Blatt mit Muster-Mails einführen |  | ros |  | ROS 05.03.2013: mache ich aus Zeitgründen jetzt nicht. | Postponed
94 | 1.2 | README | In a kick-off meeting , .. 2 Kommas zuviel …occurrence. |  | J.A. 15.10.12 |  |  | Solved
95 | 1.2 | DS | E22 "Defects found per". (Unit fehlt) |  | J.A. 15.10.12 |  | ros 17.10.2012: Sobald im MP die Unit angegeben ist, steht was Sinnvolles drin. | Rejected
96 | 1.2 |  | ROS: "Wenn Sie die Möglichkeit haben, das auszuprobieren, wäre das gut!" J.A.: "mir ist nichts besonderes aufgefallen, ich bin aber nicht sicher, welches Verhalten im Einzelnen gewollt war und bin daher vorsichtig, Aussagen zu machen. Im Screenshot sehen Sie das Ganze in LibreOffice Version 3.6.0.4 (Build ID: 932b512)." ROS: alle Kommentare scheinen gleichzeitig dargestellt zu werden, evtl. mit J.A. über Desktopsharing das Template ausprobieren. |  | J.A. 17.10.12 |  | ROS 05.03.2013: ich mache hier nichts. | Rejected
97 | 1.2 |  | Erfahrungen mit LibreOffice 3.5.4 (Ubuntu 12.04 LTS): * die Callouts sind im Weg und müssen per "Tools/Options/Calc/View/Drawing objects = Hide" abgeschaltet werden |  | J.H. 30.10.2012 |  | Snapshot s. Spalte L ROS 05.03.2013: ich mache hier nichts. | Rejected
98 | 1.2 | MP | B34 (Send Findings until ) könnte ein Auswahlfeld bekommen wie B32 und B39 |  | ros |  | ROS 05.03.2013: ich mache hier nichts. | Rejected
99 | 1.2 | MP | Evtl. "Project Manager" ersetzen durch "Receiver of Review Report" (Kommentar "typically a project manager") und "Quality Manager" durch "Receiver of Data Summary" (typically a quality manager and/or the process owner for reviews). Oder andersrum in A5/A6 Kommentare einbauen. |  | ros 26.11.2012 |  | ROS 06.03.2013: rejected, mir nicht wichtig genug. Im Buch steht übrigens: In vielen Firmen erhält der Projektleiter nach dem Review den Reviewbericht (»Review Report«) und der Qualitätsbeauftragte erhält die Kennzahlen des Reviews (»Data Summary«). | Rejected
100 | 1.2 | LoF | Spalte D (Find.Descr.) auf linksbündig (statt standard) setzen. "Problem" wirkt sich wohl nur ganz selten aus. |  | ros 28.11.2012 | minor | ROS 06.03.2013: solved | Solved
101 | 1.2 | LoF | Spalte "In Charge" soll auch Eintrag "3rd hour" enthalten. |  | ros 15.12.2012 |  | Dup. zu 111 | Duplicate
102 | 1.2 | MP | U.a. in B10, B14, B15, B18 wird Zeilenhöhe nicht automatisch angepasst, wenn Text > 1 Zeile. In B25 klappts. ROS 27.02.2013: versuche http://www.informatikserver.at/index.php/home/39/6440?format=pdf etc. |  | ros 15.12.2012 |  | ROS 28.02.2013: in MP alle Felder umgestellt außer bei den zusammengesetzten Feldern B32, B39, was ich nicht hinbekommen habe. | Solved
103 | 1.2 | DS | G66 und G71 mit nur 1 Nachkommastelle ist passender |  | ros 28.12.2012 |  | ROS 27.02.2013: solved | Solved
104 | 1.2 | MP&LoF | Wenn in MP C10 "31.12.12" eingetragen wird, dann steht nach dem Auswählen in LoF B4 nicht "31.12.12" drin. |  | ros 31.12.2012 |  | ROS 05.03.2013: C10 ff. auf Format "Text" verändert. | Solved
105 | 1.2 |  | It seems you don't use 'rules' in this example. |  | n.m. 01.01.2013 |  | ROS 27.02.2013: richtig, wir sind hier also nicht Gilb-nah | Rejected
106 | 1.2 |  | I missed the number of majors remaining… |  | n.m. 01.01.2013 |  | ROS 27.02.2013: steht in DS, "Remain. Majors" in H46 und H52 | Rejected
107 | 1.2 |  | Potential number of reviewers (10) seems to me too many for any Inspection, hence (if you agree) showing 10 lines may give a bad signal. A template is not just for use, but it also has an educational purpose. |  | n.m. 01.01.2013 |  | ROS 27.02.2013: schlechtes Signal ist richtig, aber in manchen Fällen sind mehr als 6 oder 7 nötig. Ich tendiere zum beibehalten. | Rejected
108 | 1.2 |  | Not clear what ‘Auxiliary Cells for Calculating Time Efforts’ means. |  | n.m. 01.01.2013 |  | Dup. zu 125 | Duplicate
109 | 1.2 |  | Seems I can overwrite cells that are getting their data from other cells (well, actually I can overwrite every cell). This way, I can inadvertently mess up elements of the spreadsheet. |  | n.m. 01.01.2013 |  | ROS 27.02.2013: Duplicate zu 21, dort rejected | Duplicate
110 | 1.2 |  | I miss root cause analysis. (What I ask from people is to add the 'root cause analysis' for every issue (wherever found: Inspections, tests, anywhere else). After all, all review techniques should focus on feeding prevention rather than just repair, while what I normally see is just ‘repair’. Insisting on root cause analysis helps making people aware of tendencies which helps to more explicitly prevent causing similar issues again. Small investment, fast gain.) |  | n.m. 01.01.2013 |  | ROS 27.02.2013: Argument richtig, derzeit keine Zeit das umzusetzen. Postponed | Postponed
111 | 1.2 | LoF | In Charge / Date könnte noch Einträge wie "3rd hour" oder "protocol" bekommen |  | ros 10.01.2013 |  | Dup. zu 101 ROS 27.02.2013: solved | Solved
112 | 1.2 | DS | D52 "Duplicates C": im Kommentar erwähnen, dass auch einige open Mj zu den Duplicates im Sinne von C gehören (bei Seminar am 28./29.01.2013 falsch gemacht). |  | ros 04.02.2013 |  | ROS 05.03.2013: "Caution: This is not necessarily the number of Major findings with status "duplicate"." | Solved
113 | 1.2 | DS | Zeilen 6 bis 15: für Seminar wäre praktisch, wenn die Inspektionsrate jedes Reviewers dargestellt werden würde. |  | ros 05.02.2013 |  | ROS 09.03.2013: wird nicht für Version 1.3 gemacht | Open
114 | 1.2 | README | im Blatt ReadMe werden in der Beschreibung die einzelnen Blätter wie z.B. "List of Findings" in Langform genannt aber die Abkürzungen wie "LoF" nicht erwähnt. Ich fände jeweils einen konkreten, vielleicht in Klammern, hilfreich. |  | g.t. 07.02.2013 |  | ROS 27.02.2013: rejected, weil sonst die Texte länger werden. Der Nutzen ist mir zu gering. | Rejected
115 | 1.2 |  | Eine Begleitdoku zur Handhabung, in der a) das Gesamtkonzept der Verwendung kurz beschrieben wird und b) all die hilfreichen Kommentierungen der Tabellenfelder einmal aufgelistet sind. |  | g.t. 07.02.2013 |  | ROS 27.02.2013: a) leistet Buch. b) rejected | Rejected
116 | 1.2 | README | Einen Hinweis auf den verwendeten Farbcode in den Tabellen fände ich ebenfalls sinnvoll: - weiß: hier Daten eintragen - grün: Beschriftungen mit jeweils erklärenden Kommentierungen - blau: berechnete Ergebnisse |  | g.t. 07.02.2013 |  | Dup. zu 14 ROS 09.03.2013: solved | Solved
117 | 1.2 | LoF, DS | Der Status "solved" sollte unterteilt werden in "der Autor glaubt, den Fehler behoben zu haben" und "die Fehlerbehebung wurde bestätigt". Je nach Rahmenbedingungen, Art des Fehlers und Vereinbarungen darf der Autor den Fehler selbst auf bestätigt setzen oder auch nicht. Hier kenne ich die Begrifflichkeiten fixed/closed und closed/confirmed. |  | RKN | Major | ROS 25.01.13: ernsthafter Einwand, aber Korrektur wird aufwendig. Jetziger Stand funktioniert, Vorschlag ist eine Verbesserung, keine "echter" Fehler. ROS 20.02.2013: Nicht nur "solved" müsste aufgeteilt werden, auch "rejected" und "postponed" und theoretisch "duplicate". Halte jetzigen Stand daher für besser. | Rejected
118 | 1.2 | README | CD6 entspricht nicht dem aktuellen Stand des Buches (PraxiswissenReviews_Stand2013-02-17_09h.pdf) : In 3.1 , S.21 steht: Moderator, Unterstützung durch Autor und evt. Projektleiter. |  | h.j. 27.02.13 |  | ROS 27.02.2013: nur das "evtl." ist der Unterschied. Ich mag kein "maybe" einfügen, lieber kurz bleiben. | Rejected
119 | 1.2 | README | CD9 "third hour meeting" verstehe ich, aber ist dies ein gebräuchlicher englischer Begriff? Nicht in Leo etc, aber ca. 20.000 mal in Google. |  | h.j. 27.02.13 |  | ROS 27.02.2013: Begriff in der Reviewtechnik geläufig, wird im Buch ausgeführt. | Rejected
120 | 1.2 | MP | A34: "Send Findings until " --> "Send Findings by" |  | h.j. 27.02.13 |  | ROS 27.02.2013: unsere Englischprüfer haben "until" durchgehen lassen. Halte für dt. Leser "until" besser als "by". | Rejected
121 | 1.2 | MP | C35/36: "NLOC" und "NLOC/h": sollten diese Abkürzungen im Template erklärt werden? |  | h.j. 27.02.13 |  | ROS 27.02.2013: nur im Buch | Rejected
122 | 1.2 | LoF | Unsere Einladung (s.u.) enthält die Spalten H...J nicht |  | h.j. 27.02.13 |  | ROS 27.02.2013: ok (kein Fehler bei uns, der behoben werden müsste) | Rejected
123 | 1.2 | LoF | Unser Report enthält noch weitere Spalten: "Severity after Review". Vielleicht hat sich der Reviewer geirrt? |  | h.j. 27.02.13 |  | ROS 27.02.2013: bei uns wird die Severity des Reviewers umgekippt, wollen keine extra Spalte spendieren. | Rejected
124 | 1.2 | LoF | Falls der Beitrag nicht im Rahmen des Reviews gelöst werden kann (z.B. Prozess), so gibt es noch eine Spalte, um die Nummer der Fehler im Fehler-Verfolgungssystems einzutragen. |  | h.j. 27.02.13 |  | ROS 28.02.2013: deckt postponed ("monitored in another list") ab. | Rejected
125 | 1.2 | DS | Die Tabelle ab J4 kann hilfreich sein, geht aber, soweit ich gesehen habe, nirgends in das Ergebnis ein (zumindest die Summe, O6 sehr wohl) |  | h.j. 27.02.13 |  | Dup. zu 108 | Solved
126 | 1.2 | DS | Es gibt 47 Rückmeldungen, Total (B29) nennt aber nur 43! Ursache ??? |  | h.j. 27.02.13 |  | ROS 27.02.2013: kein Fehler, siehe Kommentar B22 ("Duplicates and rejected findings not counted") | Rejected
127 | 1.2 | DS | H61: Abkürzung "ROI" erklären ? |  | h.j. 27.02.13 |  | ROS 27.02.2013: nur im Buch | Rejected
128 | 1.2 | LoF | Daher ist eine Angabe, wie die Referenz in der Rückmeldung ausgefüllt werden soll SEHR wichtig. LOF ist noch etwas schwach: Für Dokumente: Bei uns Kapitel und Seitennummer (und hier muss dies klar definiert sein, sonst gibt es Probleme beim sortieren). Oder gilt hier auch Ihre Forderung alle Reviewobjekte müssen über eine Zeilennummerierung verfügen? Das ist leider nicht immer möglich. |  | h.j. 27.02.13 |  | ROS 27.02.2013: Befund berechtigt, aber wir wollten mit den Spalten knausern. | Rejected
129 | 1.2 | MP | Abbrev. für Autor wird oft auch gebraucht, evtl. auch Abbrev. für Moderator. (Leider sieht es gestalterisch nicht gut aus, die Felder C7 und C8 wie die anderen Abbreviation-Felder zu rahmen) |  | ros 28.02.2013 |  | ROS 09.03.2013: wird nicht für Version 1.3 gemacht | Open
130 | 1.2 | README | Auf Buch verweisen: Reviews in der System- und Softwareentwicklung – Grundlagen, Praxis, kontinuierliche Verbesserung (Rösler, Schlich, Kneuper, 2013). Evtl. auch im DS ("For a description of the method see www.reviewtechnik.de/SW-QS-Tag-2010_Stichproben-Reviews_Roesler_Schlich_v1.5_pub.ppt, slides 47-50 (German only)") |  | ros 05.03.2013 |  |  | Solved
131 | 1.2 | README | In Template Maintenance Notes erwähnen, dass absichtlich keine Makros verwendet wurden. |  | ros 09.03.2013 |  |  | Solved
132 | 1.2 |  | Kommentare werden beim Öffnen manchmal an unerwarteten Positionen gezeigt (je nachdem ob oberhalb Zeilen gruppiert wurden). Vermutlich kann es gelöst werden mit Kommentar formatieren->Eigenschaften. |  | ros 09.03.2013 |  | ROS 09.03.2013: solved for README, MP, LoF, DS, RR | Solved
133 | 1.2 |  | Kommentare in LoF (Severity, Status, In Charge) werden (vermutlich wegen fixiertem Bildschirm) nicht komplett angezeigt, wenn man schon runtergescrollt hat. |  | ros 09.03.2013 |  | ROS 09.03.2013: Google "Kommentar wird bei Fixierung abgeschnitten": vermutlich ist einzige brauchbare Lösung, die Kommentare so niedrig halten, dass sie komplett in den oberen Bereich passen. Solved für Severity, genug gesolved für Status, für In Charge ist es eher egal. | Solved |  | Seve- rity
134 | [7 empty] | Open
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
Note on A1: In diesem Blatt können geplante Änderungen des Templates vorgemerkt und verfolgt werden.
Note on B2: Please use the abbreviations for the review objects.
Note on C2: The moderator may determine, how the location of a finding has to be specified. E.g. 023-026 if the finding refers to lines 23 to 26; p41 for page 41; 4.1.2 for chapter 4.1.2 If the finding occurs more than once in the review object (and it is too time-consuming to specify all locations), the wording "etc." or "ff." can be used. E.g. 023 etc.
Note on E2: If the finding was discovered via a checklist question or a scenario, please fill in the identification of this checklist question or scenario.
Note on F2: Please use the abbreviations for the reviewer names. If the finding was discovered in the review meeting, please enter "all".
Note on G2: Major: Defect, which possibly causes substantially higher costs, if it is found later in the development process. minor: Defect, which is not classified as a Major. ?: Question or the reviewer is very unsure whether the finding is a defect or a false alarm. note: Reviewer note which needs no author action. -: Used if Major, minor, ? and note are not appropriate (e.g. process improvement)
Note on H2: Meeting Comment / Action Item / Author Note (Resolution / Reason for Rejection, etc.) Field only filled if necessary
Note on I2: Open: The finding is valid and the author will deal with it in rework. Solved: The finding was solved (or no action was necessary). Rejected: The finding is rejected (false alarm). Postponed: The finding is valid but is postponed (and monitored in another list). Duplicate: The finding is the same as another finding. (This other finding is not marked as "Duplicate".) Note: exit criterion for rework: no "open" findings
Note on J2: Column for free use (please adjust the column for your special needs). Examples for use cases: - In preparation for the review meeting, the author can mark those findings with "Meeting", for which he/she needs a clarification or discussion. - In Follow-Up a reviewer can mark a finding with "t.b. re-discussed", if he/she does not agree with the author's solution.
Note on L135: Major: Defect, which possibly causes substantially higher costs, if it is found later in the development process. minor: Defect, which is not classified as a Major. ?: Question or the reviewer is very unsure whether the finding is a defect or a false alarm. note: Reviewer note which needs no author action. -: Used if Major, minor, ? and note are not appropriate (e.g. process improvement)